Evaluation of the CompreHensive geriAtRician-led MEdication Review (CHARMER) Deprescribing Intervention in Hospital: Protocol for a Cluster Randomised Stepped-Wedge Trial

Abstract

Background

Whilst almost half of older adults admitted to hospital are prescribed potentially inappropriate medicines, less than 1% have a medicine proactively deprescribed during admission in the UK. The CompreHensive geriAtRician-led MEdication Review (CHARMER) intervention, is designed to address geriatricians’ and pharmacists’ barriers and enablers to deprescribing. The CHARMER definitive trial will evaluate effectiveness, cost-effectiveness and safety.

Methods and analysis

A stepped-wedge cluster randomised controlled trial will be conducted in 20 hospitals in England, with four hospitals in reserve. All hospitals will collect baseline data. Every three months, five hospitals will be randomised to receive the intervention.

The intervention, implemented by a local project manager, comprises: A hospital action plan to set deprescribing as an organisational goal; workshops for pharmacists and geriatricians to change beliefs about deprescribing; weekly briefings between geriatricians and pharmacists to discuss opportunities for deprescribing; benchmarking reports to compare deprescribing performance across participating hospitals.

With an average 200 patients admitted and discharged during each step, the study will have 89.5% power at 5% significance level and ICC of 0.05 to detect a 3% difference in 90-day re-admission rate from 16.7% versus 13.7%.

Anonymised routinely collected data, including readmissions will be obtained for all patients admitted during the study period. Enhanced data collection periods of one month during control and intervention periods will be used to recruit patients and data for secondary outcomes and process evaluation.

Ethics and dissemination

Ethical approval for the study was obtained from Wales REC2 on 04/07/2023, REF: 23/WA/0184.

Confidential Advisory Group approval (REF: 23/CAG/0073) was obtained on 06/07/2023 to enable collection of anonymised routinely collected data for all participants during the non-enhanced data collection periods.

The research team will follow the Guide to Disseminating Research (GuiDir) framework, which includes identification of target audiences for dissemination from the outset, agreeing dissemination goals, developing a dissemination plan, choosing appropriate dissemination channels and tracking the impact of the dissemination.  Depending on the trial result the goal would ultimately be national implementation of intervention and consequently target audiences will include service commissioners and representative bodies for the different actors within the trial.

Registration

The trial was registered with ISRCTN Registry 13248281 on 21/07/2023

Strengths and limitations of this study

- Cluster-randomised stepped-wedge design trial

- Large multi-site hospital based deprescribing trial in older person’s setting

- Feasibility tested trial and theory-informed intervention

- Collation of primary outcome measure for all patients recruited onto ward to optimise likelihood of achieving target sample size

- Enhanced data collection period to obtain secondary outcome data and inform process evaluation

Keywords

Hospital, proactive deprescribing, pharmacist, consultant geriatrician, medication review, behaviour change, older adult

Introduction

Background and rationale {6a}

The World Health Organisation [WHO] Global Patient Safety Challenge: Medication Without Harm aims to reduce severe avoidable medication-related harm by 50%. [1] Polypharmacy, as a risk factor for both patient harm [2] and death, [3] is recognised as a ‘key action area’ by WHO. [1] A UK national review of prescribing in 2021, recognised the significant extent of overprescribing and recommended several primary care-based interventions to address this. [4] A meta-analysis of deprescribing interventions in primary care identified a small reduction in all-cause mortality, thereby justifying the recommendation. [5]

Whilst it is estimated that half of older people at the point of entering hospital are already prescribed at least one medicine which may be potentially inappropriate, [6] very few are stopped during admission in the UK. [7] When deprescribing does occur, it is usually in response to presenting harm i.e. it is reactive rather than proactive. [7] An opportunity to reduce overprescribing in hospital through proactive deprescribing is therefore being missed and may supplement similar activities in primary care. Hospital deprescribing trials have historically focused on process measures such as reduction in the proportion of potentially inappropriate medicines, rather than meaningful clinical outcomes. [8]

A lack of focus on addressing the barriers and enablers to deprescribing in hospitals when developing interventions may explain the lack of efficacy reported in existing deprescribing trials. [8, 9] We have used behaviour change theory to underpin the development of an intervention that is designed to address geriatricians’ and pharmacists’ capability, opportunity and motivation choose to identify opportunities to deprescribe and initiate deprescribing discussions with older people. Combined with extensive co-design work with the target audiences, [10] our approach may enhance the likelihood of good implementation fidelity and resulting effectiveness. [11]

We developed the CompreHensive geriAtRician-led MEdication Review (CHARMER) deprescribing intervention using evidence regarding the barriers and enablers to deprescribing and behaviour change theory. [10, 12, 13] CHARMER aims to facilitate geriatricians and pharmacists to identify opportunities for proactive deprescribing and initiate deprescribing conversations with older adults in hospital. The intervention comprises five components:

- A hospital action plan to set deprescribing as an organisational goal to be achieved by implementing the remainder of the CHARMER intervention components

- A geriatrician workshop with pre-prepared videos of peers navigating challenging deprescribing discussions with patients and relatives

- A pharmacist workshop with case studies to address negative beliefs about the consequences of deprescribing

- Weekly pharmacist and geriatrician briefings to identify opportunities for proactive deprescribing

- Weekly benchmarking reports on deprescribing activities to allow sites to compare their performance against other sites

In line with the UK Medical Research Council (MRC) guidance for developing and evaluating complex interventions, [14] the CHARMER intervention and trial design were feasibility tested. [15]  This led to numerous changes to both intervention implementation support and trial design, with the most significant being the decision to move from a cluster RCT to a cluster randomised stepped-wedge design. Due to the increase in power associated with a stepped-wedge design, this change requires half the number of hospitals for the trial representing more efficient trial design and thus better value for money. Furthermore, this design provides longer term follow up data in a proportion of intervention hospitals and will thereby allow us to assess whether the intervention is normalised.

Objectives

To describe the design of the definitive trial of the CHARMER hospital deprescribing intervention to evaluate its effectiveness, cost-effectiveness and safety.

Trial design

Cluster randomised stepped-wedge design trial with internal pilot. A maximum of 24 hospitals (20 active, four reserve) across England will be recruited to take part. All participating hospitals will begin the trial at the same time in a control phase.

We will step hospital sites into the intervention ‘implementation phase’ at three-month intervals (five hospitals every three months in four steps).  The intervention ‘implementation phase’ will last for three months for all hospitals; prior to transferring into the active intervention phase. Each site will therefore take part in the trial for a total of 18 months (with additional three month follow up period for data collection). This is summarised in Figure 1.

To ensure effective implementation of the intervention, a Project Manager is required at each site. This will usually be in addition to the Principal Investigator (PI), who is responsible for research delivery. Where capacity allows, the PI will be allowed to additionally assume the role of Project Manager.

Outlined here is the protocol for the main trial.  Process evaluation protocol and results papers will be published separately.

Methods: Participants, interventions and outcomes

Methods outlined below based on Protocol version V1.1 2023. The trial is registered with ISRCTN Registry 13248281. University of Leicester (rgosponsor@le.ac.uk) acted as sponsor for the trial.  They took no active involvement in either the management or delivery of the trial.

Patient and public involvement

A Patient and Public Involvement (PPI) group consisting of older adults experiencing polypharmacy (n=3) and family members/carers (n=2) are core members of the CHARMER research team. Our PPI group have contributed to the development and design of this trial, including developing the protocol, reviewing and editing participant information sheets and consent forms to ensure readability, and commenting on qualitative topic guide content. PPI group members attend weekly trial management meetings and will support the research team in the analysis, write up and dissemination of the study findings.

Trial setting

Acute hospitals in England with care of the older wards.

Eligibility criteria

Proposed inclusion and exclusion criteria for hospitals, practitioners and patients are:

Hospitals

Inclusion

- Acute hospital

- Provide an older people’s medicine service with at least one inpatient ward on which to conduct the CHARMER trial (the study ward)

- The majority of patients on the study ward(s) have a minimum length of stay of three days

- The average total monthly throughput across study ward(s) of approximately 100 patients, have at least one geriatrician (consultant or specialist registrar) and at least one ward-based pharmacist working on them

- There is an electronic prescribing system on the study ward(s)

- Hospital is willing and has the capability and capacity to implement the five components of the CHARMER intervention

- Able to provide a 0.2 whole time equivalent Project Manager to oversee implementation of the CHARMER intervention over a 14-week period (three-month implementation phase and two weeks within the active intervention phase)

- Named clinician willing and appropriate to take Principal Investigator (PI) responsibility

- Suitably trained staff e.g., sufficient research nurses, to recruit patient and personal consultee participants and enter required data

Exclusion:

- Wards that primarily host patients who are medically fit for discharge and awaiting discharge care packages

- Hospitals without a ward-based pharmacy service

- Mental health hospitals

- Hospitals that implemented the intervention in the feasibility study

Practitioners

Inclusion Criteria:

- Consultant geriatrician or specialist registrar and appropriately qualified pharmacists working across Older People’s Medicine wards

Exclusion Criteria:

- Less than 0.3 whole time equivalent of ward-based time for pharmacists

Who will take informed consent?

Hospitals will be recruited to participate through the NIHR Research Delivery Network (RDN) in England. [17] Funding to incentivise participation within hospitals is provided nationally and based on the number of enrolled patients. Consent for geriatricians and pharmacists to participate will be taken by the central research team within the Norwich Clinical Trials Unit (NCTU).

Consent for patients to provide non-routinely collected data for the enhanced data collection periods will be undertaken by local research nurses or members of the healthcare team with the relevant training in obtaining informed consent for research purposes. These individuals will usually be employed by the RDN. Any patients deemed inappropriate by the research nurses or members of the healthcare team, such as those lacking capacity or near end of life, will not be consented.

Interventions

Explanation for the choice of comparators

The control steps will consist of the provision of usual care for older people admitted to participating older people’s medicine wards.

Intervention description

The intervention is summarised in the background and described in detail in a separate publication. [10] The action plan and geriatrician and pharmacist workshops will be delivered during the three-month implementation phase. The weekly briefings and benchmarking reports will occur throughout the active intervention phase.

Criteria for discontinuing or modifying allocated interventions

There are no plans to discontinue or modify any elements of the intervention as the trial progresses.

Strategies to improve adherence to the intervention

The intervention will be delivered to geriatricians and pharmacists (the target audience) and not patients. The Project Managers have been employed to ensure that the intervention is implemented as intended and in alignment with the Trust’s standard procedures. Once the trial is complete, hospitals and participating practitioners can decide whether they wish to continue with the intervention.

Relevant concomitant care permitted or prohibited during the trial

The intervention is focused on healthcare professionals with an increase in deprescribing discussions and activity an anticipated outcome.  Patients will continue to receive all types of concomitant care during the trial with nothing prohibited.

Provisions for post-trial care

There are no provisions for post-trial care. Communication of any medicines deprescribed to primary care physicians will be undertaken as part of standard care at time of hospital discharge.

Outcomes

Selection of outcome measures was based on a previously developed core outcome set designed for hospital based deprescribing interventions. [18]The primary outcome measure was selected as hospital readmission within 90 days as this was considered to be sufficiently sensitive and proximal to the intervention.

Outcome data are summarised in Table 1. Costs and resource use, as well as economic outcomes, will be captured via expert opinion and review of study records where relevant.

Table 1	Outcome data

| Routinely collected data (without consent) | When | How |
| --- | --- | --- |
| Mortality for any reason | 90 data post-discharge | Hospital records and NHS England# Office of National Statistics Mortality records |
| Number of hospital stays* | 90 data post-discharge | Hospital records and NHS England# Hospital Episode Statistics Admitted patient care |
| Number of planned and unplanned admissions and readmissions for treatment or monitoring of health* |  |  |
| Intensive data collection (with consent) | When | How |
| Satisfaction with deprescribing process% | 2 weeks post-discharge | Postal questionnaire |
| Adverse drug events£ | 90 days post-discharge | Telephone questionnaire |
| Health Related Quality of Life (EQ-5D-5L) [19] | Pre-discharge 90 days post-discharge | Face to face on ward Telephone questionnaire |
| Primary care consultations* | 90 days post-discharge | Telephone questionnaire |
| Community pharmacy dispensed medicines* | 90 days post-discharge | NHS England# |

* Captured for additional health economic analysis purposes

** During enhanced data collection periods consent/assent for routine data collection was sought wherever possible, but where not possible, Section251 approval was applied. Where participants declined to consent/assent routine data was not collected.

# National agency responsible for collation and provision of healthcare data

% Questionnaire with 12-items  based on previously published survey tool. [20]

£ Questionnaire with 17-items inviting respondents to indicate whether or not they have experienced any of the medication related adverse events listed. The list is derived from an observational study of medication related adverse events. [21]

$To enable the outcomes regarding medication to be collated the following data will be collected:

- Name, dose and frequency of all medicines prescribed to the patient before any changes were made during the hospital admission

- Any changes made to the above medicines (stopped, dose reduction, dose increase or change in frequency)

- Name, dose and frequency of any new medicines started during the admission that are requested to be continued post discharge

Geriatrician and pharmacist participants will complete the following at the point of site set up:

- Short demographics questionnaire (Age, Gender, Ethnicity, Job-role. Grade, Training)

- Mechanism of Action questionnaire – an 11-item questionnaire measuring the extent to which the CHARMER intervention has addressed the intended four barriers and one enabler to proactive deprescribing. [15]

- Process of deprecribing questionnaire - a 19 item questionnaire capturing the extent to which practitioners underake the steps within the process of proactively deprescribing in hospital. [22]

Withdrawal

Hospitals, geriatrician and pharmacist, and patient participants will be able to withdraw from the study at any time, without providing a reason, by informing a member of the research team. If a hospital chooses to withdraw from the trial, all data collected up until the point of withdrawal will be retained and a replacement site may be recruited.

If geriatrician and pharmacist participants choose to withdraw during the trial, any data they have already contributed as participants will continue to be used. If it is feasible and the trial can progress as planned, we will work with the relevant PI to recruit a replacement geriatrician or pharmacist if one withdraws. If this is not possible e.g., study is nearing completion, we will continue the trial with the remaining geriatricians and pharmacists.

Where patients choose to withdraw, although not obliged to give a reason, a reasonable effort will be made to establish this reason, whilst remaining fully respectful of the participant’s rights. All study data collected up to the point of withdrawal will be retained.

Internal pilot

An internal pilot will be conducted with Step 1 hospitals with the following stop/go criteria:

- An average of 200 patients per hospital enrolled over 3 months (Green)

- An average of 150-199 patients per hospital enrolled over 3 months (Amber)

- Below an average of 150 patients per hospital enrolled over 3 months (Red)

If ‘Green’, the trial will proceed. ‘Amber’ it will proceed if appropriate solutions to improve recruitment are identified. ‘Red’ will require the Trial Steering Committee to make a decision regarding whether to proceed.

Participant timeline

Hospitals will participate in the trial from month zero to month twenty-one. Hospitals will be required to identify a PI responsible for local trial delivery and project manager for intervention implementation. Geriatricians and pharmacists will participate during the intervention implementation period until trial completion.

All patients admitted to the study wards under the care of a participating geriatrician will be enrolled, with permission from the national Confidentiality Advisory Group, for inclusion of their routinely collected data. This is unless they have notified the NHS in advance, of a desire to be excluded from all research activity.

Figure 1 shows how patients will be enrolled into the trial, separating out control, implementation and intervention periods.  The implementation phase is the point at which the intervention is delivered to the participating doctors and pharmacists, such that post implementation, the intervention can be delivered.

During ‘enhanced data collection periods’, patients consenting to participation on a study ward under the care of participating geriatricians, will be participants from the time of admission until three months post-discharge. We will notify the consented patient’s primary care medical practice by letter of their participation.

|  | Month |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Step: Hospital no. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 |
| 1: Hospitals 1-5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2: Hospitals 6-10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3: Hospitals 11-15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4: Hospitals 16-20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  | Control period for enrolled patients |
| --- | --- |
|  | Enhanced data collection period for consenting patients during control period |
|  | Intervention implementation phase |
|  | Intervention period for enrolled patients |
|  | Enhanced data collection period for consenting patients during intervention period |
|  | Follow up period post discharge for all enrolled patients |

Figure 1	 Schedule of Enrolment, Consent, Intervention and Data Collection

Site set up

We will provide the Project Manager and PI with a CHARMER intervention implementation handbook, developed for the feasibility study and subsequently refined.[15]  A CHARMER trial handbook, comprising instructions regarding delivering the trial and CHARMER intervention in accordance with the approved research ethics and governance processes, will be provided to the PI.

The site will be expected to conduct the trial in compliance with the approved research protocol. The PI or their delegate will be required to document and explain any deviation from the approved protocol and communicate this to the study team at NCTU.

Sample size

The underpinning feasibility study showed that recruitment to an original planned cluster randomized trial would require recruitment of over 40 hospitals and was unlikely to be achieved. Consequently, the design was changed to a stepped wedge due to the increased power provided by this design.

With a baseline step with all hospitals receiving the control followed by four separate steps, each randomising five hospitals to switch from control to intervention (20 hospitals in total) will have 89.5% power to detect a difference of 16.7% to 13.7% of 90-day re-admission rates assuming a 5% level of significance and an intra-class correlation coefficient (ICC) of 0.05 and 200 participants per hospital per step. The total sample size will be 20,000 participants. The anticipated 3% difference is similar, but slightly smaller, to the difference reported in the MedSafer study. [23]

From our feasibility study findings, we estimate that 10% of patients on study wards or consultees will provide written (or, if required, virtual) informed consent for additional patient-reported outcome data. For the enhanced data collection period, where medication changes are recorded in hospital, then if the sites collect data on 60 participants in each of the enhanced data collection periods the study would will have 99.99% power to detect an average change of 0.5 medications between the control and intervention phase, assuming a standard deviation of 1.5 medications, a 5% level of significance and an ICC of 0.05.

Recruitment

All patients receiving treatment under the care of participating geriatricians on the study wards within the study window (1st February 2024 to 31st July 2025) will be eligible for inclusion.

With national Confidentiality Advisory Group [16] permission, all patients admitted to wards under the care of participating consultant geriatricians will be enrolled for routine data collection purposes, enabling collation of the primary outcome measure for all patients. Consequently, we will not be required to enact any strategies for achieving adequate participant enrolment.

During enhanced data collection periods, one month during control period and one month during intervention period, patients admitted to wards under the care of participating consultant geriatricians will be approached to be consented for enhanced data collection i.e. non-routinely collected data needed for secondary outcome measures and process evaluation purposes. 
Assignment of interventions: allocation

Sequence generation

Sites will be randomised to the four ‘groups’, the ‘groups’ being the step at which they started the intervention. Group 1 will start the intervention on the first step, etc. A fifth group, Group 5, is the reserve list. To ensure no two sites from the same region are randomised to the same group and thereby overwhelm the local RDN team, randomisation will be stratified by region. Block size of 4 will be used so that randomisation could occur once 4 sites are recruited and concealment maintained.

Concealment mechanism

Randomisation will occur after every 4th site is recruited. If sites from the same region are participating, randomisation will be delayed until they can all be randomised at the same time. This process ensures concealment as the recruitment team will be unable to predict treatment allocation.

Implementation

The list will be generated using the Sealed Envelope online randomisation list generator. Sites will be recruited and once four sites confirm capability and capacity to deliver the research, they will be allocated to an intervention step by the trial manager using the REDCap [24] randomisation system.

Blinding

Due to the nature of the intervention and trial design blinding to allocation is not possible.

Data collection and management

Plan for assessment and collection of outcomes

We will collect relevant outcome data at two levels for patients admitted to study wards and under the care of participating consultant geriatricians:

1) routinely collected data for all patients admitted for the duration of control and intervention steps, i.e., 18 months.

2) non-routinely collected data during ‘enhanced data collection periods’ which take place for four weeks during both the control and intervention period.

Routine data will be collected by nurses employed within the national RDN [25] for all patients under the care of a participating geriatrician admitted to the study wards during the trial period and provided anonymously to the research team following national Confidentiality Advisory Group (CAG) [16] permission to collect these data without the requirement for patient consent.

Plans to promote participation retention and complete follow-up

With enrolment of all patients and collation of routinely collected data there are no plans to promote participation retention for the purposes of the primary outcome measure.

Due to the short duration of the follow-up period, three months (90 days) following discharge, the likelihood of drop-out by patients is minimal. However, as participants will be followed up in the community post-discharge, there is a potential for loss to follow-up. Participants who agree to complete the study questionnaires will be asked to provide contact information to be contacted at the three-months follow-up time point – telephone, postal address and/or email. Patients who do not respond to contact requests to complete follow-up questionnaires by telephone will be considered as lost to follow-up for the purposes of questionnaire completion. However, routine clinical data will still be collected from patient records. Data will be retained for analysis.

Data management

Data will be entered under the participant’s Identification number onto the central database stored on NCTU servers. Access to the database will be via unique, individually assigned usernames and passwords, and only accessible to members of the CHARMER research team NCTU, and external regulators if requested. The servers are protected by firewalls and are patched and maintained according to best practice. The physical location of the servers is protected physically and environmentally in accordance with University of East Anglia’s General Information Security Policy 3 (GISP3: Physical and environmental security).

The database has been developed by NCTU Data Management using REDCap, [24] in conjunction with the CHARMER trial team. The database software provides several features to help maintain data quality, including maintaining an audit trail, allowing custom validations on all data, allowing users to raise data query requests, and data quality rules to identify validation failure/ missing data.

After completion of the study, the database will be retained on the servers of NCTU for ongoing analysis of secondary outcomes.

Confidentiality

All data will be sent to the Clinical Trials Unit which will be responsible for data analysis. Data will be stored in password protected computers and only shared in an anonymous format with the wider research team.

Statistical methods for primary and secondary outcomes

Characterising and Comparing Sites

Participating hospitals and geriatricians and pharmacists will be characterised using descriptive statistics from the hospital site profile questionnaire and practitioner participant demographic questionnaire. Data will be visually compared with data captured from NHS Improvement’s hospital provider level benchmarking tool ‘model hospital’ [26] regarding the number and cost of staff on medicine for older people’s medicine wards. Demographic characteristics of patients between all study wards of the participating hospitals will be visually compared to explore whether they are comparable.  For the sample of patients in the study cohort from whom consent is obtained either from the patient or consultee for additional non-routine data to be collected, the demographic characteristics of this group will be visually compared with the wider study cohort. This will establish whether the sub-set of patients for whom additional data are collected, are a good representation of the patient cohort in the study.

Main effectiveness analysis

The primary analysis will be using intention-to-treat with a pre-specified statistical analysis plan agreed prior to analysis. Analysis will be at the patient level and include data from all patients.

Unplanned readmission at 90 days, primary outcome measure, will be compared between the treatment and control groups using a logistic mixed regression model with hospital included as a random effect, and fixed factors will include randomisation arm and time period. If a significant number have more than one readmission, then a Poisson or Negative binomial model will be used as a secondary analysis. The assumptions of the models will be checked and if appropriate a Generalised Estimating Equation approach will be used if the random effect is not normally distributed, or a non-parametric bootstrap approach will be will be used to account for missing data.

Interim analyses

No interim analyses will be performed as the primary outcome measure will only be available once the trial is complete. The intervention is behavioural and focused on healthcare professionals, consequently it was believed to not be necessary to access the primary outcome data, relating to rehospitalisation, until the trial was completed.

Additional analyses

A sensitivity analysis will adjust for relevant baseline characteristics e.g. age, and the number of pre-admission medicines.

The number of medications stopped during the enhanced data collection period will be compared between the control and intervention using a linear mixed model including hospital as a random effect, and fixed factors will include randomisation arm and time period.

The proportion of patients per arm where a pre-admission medicine is proactively deprescribed will be compared using logistic regression, the same model as above.

The QoL measures will be compared between the control and intervention using a linear mixed model including hospital as a random effect, and fixed factors will include randomisation arm and time period.

Handling missing data

Due to the use of routinely collected data it is unlikely that there will be significant missing data for the main analysis. If appropriate, we will use imputation to account for missing data for other non-routine outcomes.

A full statistical analysis plan (SAP) will be written prior to the start of any data analysis. As the SAP will be more detailed any discrepancies in the analysis between the SAP and the protocol, the SAP will take priority.

Health Economics

A within trial economic evaluation will be undertaken from the NHS perspective to estimate whether deprescribing is cost-effective.

Resources associated with providing the PDX intervention will be included in the evaluation. This will include staff time required for activities such as attending workshops, watching video material, attending briefings, preparing an action plan, and preparing benchmarking reports. The intervention may have on resource use associated with NHS inpatient admissions in the follow-up period, as well as medicines use, will also be investigated. For the consented sub-sample, data relating to HRQoL (EQ-5D-5L) and primary care contacts will also be collected.

Resource use data collection has been informed by lessons learnt from the feasibility study. The occurrence of activities related to the intervention, such as attendance at workshops, will be recorded by means of the fidelity framework conducted as part of the process evaluation. The protocol for the process evaluation will be reported separately.

The resource implications of these events will be costed by means of information obtained from the fidelity framework as well as additional insights gained from aspects of the feasibility study, e.g., qualitative research. Where necessary, we will elicit further information required to cost the intervention. For example, eliciting expert opinion on the typical time required for deprescribing activities.

In terms of NHS resource use data will be obtained from NHS England related to inpatient admissions and prescribing data. Additionally, data relating to the initial (recruitment) inpatient stay will be obtained from study sites. The feasibility study indicated that primary care related resource use would be difficult to collect by the methods originally planned, namely either interviews with GPs/other primary care members with a prescribing role or general practice patient records review, without adding substantially to the burden of the study. For this reason, a bespoke section was added to the drug adverse event questionnaire to collect details of the participating patient’s participant primary care use at the 90-day follow-up telephone interview. The proposed questions have been shared with the trial management team and Patient and Public Involvement (PPI) members for comment. These data would be collected from the consented sub-study only. Resources identified will be combined with appropriate unit costs data, e.g., NHS reference costs[11], to estimate the mean overall cost in each study-arm. This will enable an estimate of any differences in the cost of the de-prescribing group compared to usual care.

The primary health economics analysis will be a cost-effectiveness study using the studies primary outcome of re-admissions in the 90-day follow-up period. As part of the trial, we will collect measures of HRQoL using EQ-5D-5L. [19] These will be collected in the consented sub-sample at baseline and at 90 days post-discharge, either by self-report or proxy response. This measure can be used to estimate quality adjusted life years (QALY), enabling the mean difference in QALY scores to be estimated (incremental effect). This will be carried out for the consented sub-sample and will be presented as a sensitivity analysis. As part of the analysis, we will explore whether it is sensible to use these values to impute QALY scores for the whole sample, if carried out this will also be presented as an additional sensitivity analysis.

If the intervention arm is both less expensive e.g., due to lower medication or readmissions costs, and more effective than usual care in terms of the primary outcome of re-admissions at 90 days then it would be said to dominate usual care and would be the preferred option. If neither the intervention nor the usual care is clearly preferred; we will estimate incremental cost-effectiveness ratios (ICERs) in terms of cost per re-admission prevented.[12] The associated level of uncertainty will be characterised by estimating cost-effectiveness acceptability curves (CEACs). Sensitivity analysis will also be undertaken to assess the robustness of results to changes in key assumptions. In line with the outcome analysis, all analyses will be conducted on an intention-to-treat basis. Appropriate actions will be taken where there is missing data, for example imputing data by means of multiple imputation. As part of the health economic analysis a health economics analysis plan (HEAP) will be written, in consultation with the CI and trial statistician and shared with team members.

A health economic model will be constructed to explore the effects of long-term changes in prescribing costs and mortality. The exact form of this model will be established in consultation with other members of the research team, as a clinical input to this process would be vital. A priori,this would be expected to take the form of a Markov model estimating cost per quality adjusted life year.

Data sharing

The protocol will be available on the NIHR website and within the ISRCTN register. The datasets generated during and/or analysed during the current study are not expected to be made available due to data sharing restrictions as part of section 251 approval and NHS England governance requirements. Statistical code will be available upon request from allan.clark@uea.ac.uk.

# Oversight and monitoring

NCTU are responsible for managing the trial including operational delivery, data management, statistical analysis, health economics and quality assurance.

The Trial Steering Committee responsible for overseeing the CHARMER research programme will take on the responsibilities of the Trial Steering Committee and Data Management Committee at the beginning of the trial. The committee consists of a research active consultant geriatrician (Chair), national lead for provision of clinical pharmacy services, senior medical statistician, senior clinical trialist, senior behavioural scientist and two PPI members, which are all independent of the sponsor and have no competing interests. The Committee was convened to meet approximately six monthly at key timepoints. Prof Bhattacharya (Co-CI and award holder) and Clark (Trial Statistician) are non-independent members. At least two representatives from NCTU, the funding award body, sponsor and trial team attend as observers reporting on progress and advising as requested.

As the primary outcome (readmissions to hospital) is obtained from routine data retained by NHS Digital and would not be available to the research team until after the last patient has completed, it was not possible to review the safety of the intervention during the trial.

Adverse event reporting and harms

Adverse events are not being collected for this trial. Potential unintended harms arising from the intervention with respect to deprescribing discussions or the stopping or reducing medications will be assessed by questionnaire in those participants who consent or for whom consultee assent is provided in the post-intervention enhanced data collection period. Harms identified will be reviewed by clinician members of the trial management group, categorised and reported as part of the trial publication. Complaints from participants, consultees, relatives or staff relating to the trial conduct will be directed to the Sponsor. NCTU will lead on investigating complaints in conjunction with the Trial Management Groups and Sponsor.

Frequency and plans for auditing trial conduct

The delivery of the trial is overseen by NCTU Quality Assurance team (who are independent of the research team and Sponsor) on a quarterly basis. Should issues arise, a risk-based audit may be undertaken at site or coordinating centre level.

Communication of protocol amendments

Ethics (and Confidential Advisory Group) approval will be sought for all protocol amendments. Approved amendments will be communicated to participating sites including investigators, and where necessary trial participants. [SPIRIT guidance: Plans for communicating important protocol modifications (e.g., changes to eligibility criteria, outcomes, analyses) to relevant parties (e.g., investigators, REC/IRBs, trial participants, trial registries, journals, regulators).]

### Ethics and dissemination

Ethical approval for the study was obtained from Wales REC2 on 04/07/2023, REF: 23/WA/0184.

Confidential Advisory Group approval (REF: 23/CAG/0073) was obtained on 06/07/2023 to enable collection of anonymised routinely collected data for all participants during the non-enhanced data collection periods.

The research team will follow the Guide to Disseminating Research (GuiDir) framework, which includes identification of target audiences for dissemination from the outset, agreeing dissemination goals, developing a dissemination plan, choosing appropriate dissemination channels and tracking the impact of the dissemination. [27]  Depending on the trial result the goal would ultimately be national implementation of intervention and consequently target audiences will include service commissioners and representative bodies for the different actors within the trial.

### Funding statement

The project was funded by the National Institute for Health and Care Research, through the Programme Grant for Applied Research funding stream. Grant number 200874.

### Availability of data and materials

The final trial dataset approved for sharing will be available upon request from Bhattacharya and University of Leicester Sponsor’s Office. A data sharing agreement will be required between the requesting organisation and the University of Leicester. Under section 251 and NHS England contracts, it will not be possible to share individualised data provided by NHS England.

### Competing interests

DW undertook consultancy work for Rosemont Pharmaceuticals and Desitin Pharma during the study period. All other authors report no competing interests.

### Word count (excluding Tables and Figures): 5,292

References

1.	World Health Organization. Global Patient Safety Challenge: Medication Without Harm 2017 [Available from: http://apps.who.int/iris/bitstream/10665/255263/1/WHO-HIS-SDS-2017.6-eng.pdf?ua=1&ua=1.

2.	Zaninotto P, Huang YT, Di Gessa G, Abell J, Lassale C, Steptoe A. Polypharmacy is a risk factor for hospital admission due to a fall: evidence from the English Longitudinal Study of Ageing. BMC Public Health. 2020;20(1):1804.

3.	Leelakanok N, Holcombe AL, Lund BC, Gu X, Schweizer ML. Association between polypharmacy and death: A systematic review and meta-analysis. J Am Pharm Assoc (2003). 2017;57(6):729-38.e10.

4.	Ridge K. National overprescribing review report: Good for you, good for us, good for everybody: A plan to reduce overprescribing to make patient care better and safer, support the NHS, and reduce carbon emissions: Department of Health and Social Care.,; 2021 [Available from: https://www.gov.uk/government/publications/national-overprescribing-review-report.

5.	Bloomfield HE, Greer N, Linsky AM, Bolduc J, Naidl T, Vardeny O, et al. Deprescribing for Community-Dwelling Older Adults: a Systematic Review and Meta-analysis. J Gen Intern Med. 2020;35(11):3323-32.

6.	Gallagher P, Lang PO, Cherubini A, Topinková E, Cruz-Jentoft A, Montero Errasquín B, et al. Prevalence of potentially inappropriate prescribing in an acutely ill population of older patients admitted to six European hospitals. Eur J Clin Pharmacol. 2011;67(11):1175-88.

7.	Scott S, Clark A, Farrow C, May H, Patel M, Twigg MJ, et al. Deprescribing admission medication at a UK teaching hospital; a report on quantity and nature of activity. Int J Clin Pharm. 2018;40(5):991-6.

8.	Thillainadesan J, Gnjidic D, Green S, Hilmer SN. Impact of Deprescribing Interventions in Older Hospitalised Patients on Prescribing and Clinical Outcomes: A Systematic Review of Randomised Trials. Drugs Aging. 2018;35(4):303-19.

9.	Hansen CR, O'Mahony D, Kearney PM, Sahm LJ, Cullinan S, Huibers CJA, et al. Identification of behaviour change techniques in deprescribing interventions: a systematic review and meta-analysis. Br J Clin Pharmacol. 2018;84(12):2716-28.

10.	Scott S, Atkins B, Kellar I, Taylor J, Keevil V, Alldred DP, et al. Co-design of a behaviour change intervention to equip geriatricians and pharmacists to proactively deprescribe medicines that are no longer needed or are risky to continue in hospital. Res Social Adm Pharm. 2023;19(5):707-16.

11.	Albarracín D, Gillette JC, Earl AN, Glasman LR, Durantini MR, Ho MH. A test of major assumptions about behavior change: a comprehensive look at the effects of passive and active HIV-prevention interventions since the beginning of the epidemic. Psychological bulletin. 2005;131(6):856-97.

12.	Scott S, May H, Patel M, Wright DJ, Bhattacharya D. A practitioner behaviour change intervention for deprescribing in the hospital setting. Age and Ageing. 2020.

13.	Scott S, Twigg MJ, Clark A, Farrow C, May H, Patel M, et al. Development of a hospital deprescribing implementation framework: A focus group study with geriatricians and pharmacists. Age Ageing. 2019;49(1):102-10.

14.	Skivington K, Matthews L, Simpson SA, Craig P, Baird J, Blazeby JM, et al. A new framework for developing and evaluating complex interventions: update of Medical Research Council guidance. Bmj. 2021;374:n2061.

15.	Scott S, Atkins B, Martin-Kerry JM, Pritchard M, Alldred DP, Clark AB, et al. CompreHensive geriAtRician-led MEdication Review (CHARMER): protocol for a feasibility study of a hospital deprescribing behaviour change intervention. BMJ Open. 2023;13(8):e075795.

16.	NHS Health Research Authority. Confidentiality Advisory Group 2025 [Available from: https://www.hra.nhs.uk/about-us/committees-and-services/confidentiality-advisory-group/.

17.	Clinical Research Network  [Available from: https://www.nihr.ac.uk/explore-nihr/support/clinical-research-network.htm.

18.	Martin-Kerry J, Taylor J, Scott S, Patel M, Wright D, Clark A, et al. Developing a core outcome set for hospital deprescribing trials for older people under the care of a geriatrician. Age Ageing. 2022;51(11).

19.	EQ-5D. EQ-5D-5L | Available modes of administration 2022 [Available from: https://euroqol.org/eq-5d-instruments/eq-5d-5l-available-modes-of-administration/.

20.	Reeve E, Shakib S, Hendrix I, Roberts MS, Wiese MD. Review of deprescribing processes and development of an evidence-based, patient-centred deprescribing process. Br J Clin Pharmacol. 2014;78(4):738-47.

21.	Schoenmakers TW, Teichert M, Wensing M, de Smet PA. Evaluation of Potentially Drug-Related Patient-Reported Common Symptoms Assessed During Clinical Medication Reviews: A Cross-Sectional Observational Study. Drug Saf. 2017;40(5):419-30.

22.	Scott SB, N.; Bhattacharya, D. An Internationally Derived Process of Healthcare Professionals’ Proactive Deprescribing Steps and Constituent Activities. Pharmacy. 2024;12:138.

23.	McDonald EG, Wu PE, Rashidi B, Wilson MG, Bortolussi-Courval É, Atique A, et al. The MedSafer Study-Electronic Decision Support for Deprescribing in Hospitalized Older Adults: A Cluster Randomized Clinical Trial. JAMA Intern Med. 2022;182(3):265-73.

24.	REDCap. Research Electronic Data Capture  [Available from: https://projectredcap.org/software/.

25.	NIHR: National Institute for Health and care Research. Research Delivery Network: The Research Delivery Network (RDN) enables the health and care system to attract, optimise and deliver research across England. 2025 [Available from: https://www.nihr.ac.uk/support-and-services/support-for-delivering-research/research-delivery-network.

26.	NHS England. The Model Health System  [Available from: https://www.england.nhs.uk/applications/model-hospital/#:~:text=The%20Model%20Health%20System%20is,continuously%20improve%20care%20for%20patients.

27.	Scott S, Atkins B, D'Costa T, Rendle C, Murphy K, Taylor D, et al. Development of the Guide to Disseminating Research (GuiDiR): A consolidated framework. Research in Social and Administrative Pharmacy. 2024;20(11):1047-57.